# PHLPOST Document Tracking System: Development Plan

Internal document routing, approval and audit system. Rebuild of the prototype on the restructured schema (Document, Version, Route, RouteStep, Transmittal, AuditLog). Planned for one full-stack developer working solo.

## 1. Document control

| Field | Value |
| --- | --- |
| Project | PHLPOST Document Tracking System v2 |
| Document version | 0.2 (solo developer plan) |
| Prepared | 2026-10-14 |
| Developer (design, backend, frontend, deployment) | ____ |
| Client sponsor | ____ |
| Client contact for decisions and UAT | ____ |
| Hours available per week | ____ |
| Planned start | YYYY-MM-DD |
| Planned go-live | YYYY-MM-DD |
| Status | Draft, awaiting client review |

### Revision history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0.1 | 2026-10-14 | ____ | Initial plan |
| 0.2 | 2026-10-14 | ____ | Re-planned for one full-stack developer: scope tiers, vertical slices, longer estimates, leaner documentation |
|  | YYYY-MM-DD |  |  |

## 2. Purpose and scope

Goal: track every document passing through every department, from creation to completion, with a full custody trail.

Core scenario the system must support: Department X creates a document and routes it to Office A and Office B for signature (or other actions). Each office acts in turn. When all steps are done, the document returns to the origin office as completed. If any office rejects or returns it, it goes back to the origin for revision and can be resubmitted as a new routing round.

### Scope tiers

Build in this order. If time runs short, cut from the bottom of the list, never from Must. The schema already leaves room for the Later tier (for example a nullable parallel_group on route steps), so adding it later needs no rebuild.

| Tier | Features | Target release |
| --- | --- | --- |
| Must | Login and roles; user and department admin; documents with files and versions; sequential routing across offices (submit, receive, approve, reject, return, recall, resubmit); transmittal log; audit log; in-app notifications; due dates and overdue flag; My Docs, inbox and tracking by reference number | v1.0 go-live |
| Should | Search and filters; archive and retention date; hash-chain verification screen; email notifications; admin for action codes and document types; one simple report | v1.0 if time allows, otherwise v1.1 |
| Later | Parallel routing groups; SSO or Active Directory; access grants and confidentiality levels; reports and analytics; QR or barcode for paper copies; certificate-based signatures | v1.2 and beyond |

Out of scope: mobile app, external (non-staff) users, OCR or full-text search inside files, integration with other PHLPOST systems.

## 3. How this plan works for one developer

- Build vertical slices. Each phase delivers one thin working path through database, API and screen, not one layer at a time.

- Get to a demo early. The core scenario runs end to end at Milestone M4, so the client's feedback arrives before the polish work.

- Timebox every phase. If a phase passes 125% of its estimate, drop its cut-first items instead of moving the date.

- Estimate in focused weeks. One focused week is about 30 build hours; meetings, support and admin take the rest of a 40-hour week.

- Keep one task in progress. Finish and merge it before starting the next; one backlog list, one board.

- Automate what a team would split between people: CI, migrations, a generated API client, scripted deploys and nightly backups.

- Guard against being the only person who knows the system. Write short decision notes as you go, keep the README and runbook current, and keep code, credentials and backups in accounts the client can reach.

- Use the client as reviewer. A demo and written approval at each milestone replaces a second developer's review for requirement mistakes.

## 4. Success criteria

- A user can create, route, act on, return and complete a document end to end without developer help.

- Every state change produces a transmittal entry and, where relevant, an audit entry, written in the same transaction.

- No file changes after upload without producing a new version with a new hash.

- Users only see documents their role and department allow.

- Overdue steps are visible to the approver and the origin office.

- UAT is signed off by the client with no open critical or high defects.

- Someone else can set up and run the system from the README and runbook alone.

## 5. Open decisions to settle with the client

Phase 0 closes when each decision has an answer or the client accepts the default. An unanswered decision does not block the build: the default is built and changed later if needed.

| # | Decision | Options | Default if unanswered | Answer | Date |
| --- | --- | --- | --- | --- | --- |
| D1 | Route order | Sequential only, or sequential plus parallel groups | Sequential only |  |  |
| D2 | What signed means | Recorded approval click, signature image on PDF, digital certificate | Recorded approval, optional signed file as a new version |  |  |
| D3 | Rejection behavior | Back to origin, or back to previous step | Back to origin |  |  |
| D4 | Physical copies | Digital only, or paper tracked by QR or barcode | Digital only |  |  |
| D5 | Confidential documents | Visible to route participants only? Who else? | Route participants, origin office and Records role |  |  |
| D6 | Sign-in method | Local accounts, or SSO / Active Directory | Local accounts |  |  |
| D7 | Retention periods | Per document type | A retention date field, no automatic disposal |  |  |
| D8 | Email notifications | In-app only, or in-app plus email (SMTP available?) | In-app only |  |  |
| D9 | Hosting | On-premise server, or cloud; file storage location (NAS?) | One server, file path set by configuration |  |  |

## 6. Technology and environments

| Layer | Choice |
| --- | --- |
| Frontend | Vue 3, Vue Router, Pinia, Tailwind, Heroicons, Axios (existing prototype is reused) |
| Backend | Spring Boot, Spring Security, Spring Data JPA, Lombok |
| Database | PostgreSQL (MySQL also works); schema managed by Flyway migrations; Hibernate ddl-auto turned off |
| API contract | OpenAPI generated by springdoc; TypeScript types and client generated from it, so the frontend cannot drift from the backend |
| File storage | Local or NAS path outside the web root: documents/YYYY/MM/DD/{id}_{name} |
| Local setup | Docker Compose starts database, mail catcher and app with one command |
| CI | GitHub Actions or equivalent: build, tests and lint on every push |
| Deployment | One server or VM, Docker Compose, reverse proxy with TLS, scripted deploy, nightly database and file backup to a second location |
| Backlog and notes | One board (GitHub Projects or Trello) and short decision notes in /docs |

Two environments are enough for one developer: Staging doubles as the demo and UAT environment.

| Environment | Purpose | URL | Notes |
| --- | --- | --- | --- |
| Local | Daily development | localhost | Docker Compose |
| Staging | Demos and UAT, production-like | ____ | Deployed on every merge to main |
| Production | Live | ____ | Deployed by script after a Staging check |

## 7. Roadmap overview

Estimates are in focused weeks (about 30 build hours each) for one developer. Fill in the dates once the start date is set.

| Phase | Name | Focused weeks | Start | End | Milestone | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 0 | Discovery and sign-off | 1 | YYYY-MM-DD | YYYY-MM-DD | M0: Scope approved | Not started |
| 1 | Foundation and API contract | 1.5 | YYYY-MM-DD | YYYY-MM-DD | M1: Skeleton running on Staging | Not started |
| 2 | Authentication, users and roles | 2 | YYYY-MM-DD | YYYY-MM-DD | M2: Secure login and roles | Not started |
| 3 | Documents and file versions | 2.5 | YYYY-MM-DD | YYYY-MM-DD | M3: Create and view documents | Not started |
| 4 | Routing engine | 4 | YYYY-MM-DD | YYYY-MM-DD | M4: Core scenario demo, end to end | Not started |
| 5 | Transmittal and audit logging | 2 | YYYY-MM-DD | YYYY-MM-DD | M5: Full traceability | Not started |
| 6 | Notifications and due dates | 1.5 | YYYY-MM-DD | YYYY-MM-DD | M6: Alerts and overdue tracking | Not started |
| 7 | Should tier features | 3 | YYYY-MM-DD | YYYY-MM-DD | M7: Feature complete | Not started |
| 8 | Hardening and UAT | 2.5 | YYYY-MM-DD | YYYY-MM-DD | M8: UAT sign-off | Not started |
| 9 | Deployment and go-live | 1 | YYYY-MM-DD | YYYY-MM-DD | M9: Live, then hypercare | Not started |
|  | Total | 21 |  |  |  |  |
|  | Buffer (20%) | about 4 |  |  |  |  |
|  | Total with buffer | about 25 |  |  |  |  |

### Calendar time by working hours

| Hours per week on this project | Calendar time for 21 focused weeks plus buffer |
| --- | --- |
| 30 or more (full time) | about 25 weeks |
| 20 (three days a week) | about 38 weeks |
| 10 (alongside other work) | about 76 weeks: trim to the Must tier or add a second person |

At full time, the first end-to-end demo (M4) lands about 13 weeks in. Every phase ends with a demo on Staging and a written client approval.

## 8. Phase details

Each phase is a thin vertical slice. A phase is done only when every exit criterion is met. Cut-first items are dropped before the date moves.

### Phase 0: Discovery and sign-off (1 week)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: agree what v1.0 contains before writing code.

Tasks

- ☐ Walk the client through the core scenario and the proposed schema.

- ☐ Settle decisions D1 to D9, or record that the default is accepted.

- ☐ Write one-page requirements and a user story with acceptance criteria for each role (Staff, Approver, Records, Admin).

- ☐ Draw the status and routing state machine.

- ☐ Mark each prototype screen as keep, adapt or replace.

- ☐ Book the demo and UAT dates with the client now.

Deliverables: one-page requirements, user story backlog, state machine diagram, decision log, approved scope tiers.

Exit criteria: client approves the Must tier in writing (email is enough); demo and UAT dates are in both calendars.

### Phase 1: Foundation and API contract (1.5 weeks)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: a working skeleton that builds, tests and deploys itself, so later phases only add features.

Tasks

- ☐ Repository, branch rules and CI pipeline.

- ☐ Docker Compose for local setup; Staging environment.

- ☐ Flyway baseline migration for the new schema; turn off ddl-auto.

- ☐ Per-environment configuration; secrets kept outside the repository.

- ☐ Global error format, validation, logging, health endpoint.

- ☐ Request and response DTOs for all entities, published as OpenAPI; generate the TypeScript client.

- ☐ Seed script: departments, test users, action codes.

- ☐ Frontend: src/api/ layer, shared axios instance, remove starter scaffolding and duplicate components.

Cut first: request IDs in logs.

Deliverables: skeleton running locally and on Staging, OpenAPI v1, README with setup steps.

Exit criteria: you can wipe everything and rebuild a working local environment from the README in 30 minutes; CI is green.

### Phase 2: Authentication, users and roles (2 weeks)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: nobody reaches any data without logging in, and each role sees only its own actions.

Tasks

- ☐ Login and logout (JWT or session); BCrypt password hashing.

- ☐ Replace the CurrentUserService stand-in and permitAll() with real authorization.

- ☐ Roles: Staff, Approver, Records, Admin; checks in the service layer.

- ☐ Basic admin screens for departments and users, including admin password reset.

- ☐ Frontend: login page, auth store, route guards, axios token interceptor, role-aware sidebar.

- ☐ Audit entries for login, logout and failed attempts.

Cut first: account lockout, self-service password reset.

Deliverables: RBAC matrix (one table), working login flow.

Exit criteria: every endpoint rejects unauthenticated calls; role tests pass; an admin can create departments and users.

### Phase 3: Documents and file versions (2.5 weeks)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: a user can create a draft document, attach a file and see its version history.

Tasks

- ☐ Create and edit documents in DRAFT status (replaces the Draft table).

- ☐ Reference numbers: department code, year, running counter.

- ☐ Upload with size and type limits, SHA-256 hash, storage outside the web root, authenticated download.

- ☐ Document versions (original, revision, signed) and version history.

- ☐ Frontend: Create Document (details and file), My Docs, Document detail with versions card and comments.

- ☐ Audit entries for view, download and upload.

Cut first: multiple supporting attachments (ship one main file first), in-browser file preview.

Deliverables: document and version endpoints, updated screens, storage notes in the README.

Exit criteria: a user can create a draft, attach a file, see its hash and versions, and download it; an unauthorized user cannot.

### Phase 4: Routing engine (4 weeks)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: the core scenario works end to end. This is the riskiest phase, so it gets the most time.

Tasks

- ☐ Route and RouteStep model, sequential order only (the parallel_group column exists but is unused).

- ☐ Actions: submit, receive, approve, reject, return for revision, recall, resubmit as a new round, complete.

- ☐ One state machine class owns every status change; document status is derived from steps, never set directly.

- ☐ The API returns allowedActions for the current user on each document.

- ☐ Optimistic locking so two people cannot act on the same step.

- ☐ Frontend: route builder, route progress card, action dialog (approve with remarks, reject with a required reason), Awaiting My Action inbox, dashboard counters.

- ☐ Unit tests for every transition.

Cut first: recall, signed-file upload on approval (start with a plain recorded approval).

Deliverables: state machine specification, routing endpoints, updated screens, transition tests.

Exit criteria: X to A to B to X runs end to end, including a rejection and a resubmission; illegal transitions are blocked and tested. Demo to the client (Milestone M4).

### Phase 5: Transmittal and audit logging (2 weeks)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: every action leaves a tamper-evident record.

Tasks

- ☐ A transmittal entry for every routing event, with a transmittal number, written in the same transaction as the action.

- ☐ Hash chain: each entry stores the previous hash and its own.

- ☐ Database permissions: the application account cannot update or delete transmittal rows.

- ☐ A verification command that re-checks the whole chain.

- ☐ Audit coverage review: login, view, download, denied access, role changes, with IP and user agent.

- ☐ Frontend: Transmittal log with filters, per-document timeline, File Integrity page.

Cut first: the verification screen (keep the command-line check).

Deliverables: logging policy (one page), verification command, updated screens.

Exit criteria: editing a transmittal row by hand is detected by the verification command; every action in the RBAC matrix has an audit or transmittal record.

### Phase 6: Notifications and due dates (1.5 weeks)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: offices find out what is waiting for them, and late items stand out.

Tasks

- ☐ In-app notifications for assigned, completed, rejected and recalled events.

- ☐ Due dates on steps, an overdue flag, a scheduled reminder job.

- ☐ Frontend: working bell and unread badge, Notifications page, overdue indicators.

Cut first: escalation to the department head.

Deliverables: notification catalogue (event, recipient, message).

Exit criteria: each event in the catalogue notifies the right people exactly once; overdue steps are flagged and reminded.

### Phase 7: Should tier features (3 weeks)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: add the Should tier in order of client value, and stop when the three weeks are spent. Anything left becomes the v1.1 backlog.

Tasks

- ☐ Search and filters (reference number, title, type, department, status, date range) with pagination.

- ☐ Archive as a separate flag, retention date, soft delete only.

- ☐ Email notifications, if D8 requires them.

- ☐ Admin for action codes and document types.

- ☐ One simple report: documents by status and overdue steps.

Cut first: the report, then admin for document types.

Deliverables: feature-complete build on Staging, v1.1 backlog.

Exit criteria: all Must items done; each Should item is either done or moved to the v1.1 backlog with the client's agreement.

### Phase 8: Hardening and UAT (2.5 weeks)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: find the problems before the client's users do.

Tasks

- ☐ Full regression run, a pass through the OWASP top 10 checklist, dependency vulnerability scan.

- ☐ Seed a realistic volume (for example 50,000 documents) and check list and search speed.

- ☐ Browser checks on the browsers the client actually uses.

- ☐ UAT with real users following written scripts; triage and fix defects.

- ☐ Backup and restore test.

- ☐ Optional: pay a peer or contractor for a one-day code and security review, since nobody else reads the code.

Cut first: performance tuning beyond the slowest screens.

Deliverables: test report, UAT sign-off form, known issues list.

Exit criteria: no open critical or high defects; the client signs UAT.

### Phase 9: Deployment and go-live (1 week)

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Goal: the system is live, users are trained, and support is agreed.

Tasks

- ☐ Production environment, TLS, backups, uptime monitoring.

- ☐ Set up departments, users, action codes and document types; migrate existing records if any.

- ☐ Training session; hand over the user manual and admin guide.

- ☐ Go-live checklist and rollback plan.

- ☐ Reserve two weeks after go-live for hypercare, and agree a support contact and response times in writing.

Cut first: extra training sessions (record one video instead).

Deliverables: runbook, rollback plan, release notes v1.0.

Exit criteria: system live; hypercare issues tracked; handover accepted.

## 9. Documentation set

Keep documentation light and close to the code. Most of it lives in the repository (/docs) or is generated. Write each item in the phase shown, not at the end.

| Document | Where it lives | Phase | Due | Status |
| --- | --- | --- | --- | --- |
| Requirements and user stories | One page plus the backlog board | 0 | YYYY-MM-DD |  |
| Decision log | Section 13 of this plan | 0 onward | YYYY-MM-DD |  |
| State machine specification | Mermaid diagram in /docs | 0, refined in 4 | YYYY-MM-DD |  |
| ERD and data dictionary | Mermaid ERD in /docs, column notes in the migrations | 1 | YYYY-MM-DD |  |
| API contract | Generated OpenAPI, no manual document | 1, regenerated each phase | YYYY-MM-DD |  |
| Decision notes (ADRs) | One short paragraph each in /docs/adr | 1 onward | YYYY-MM-DD |  |
| README and setup guide | Repository root, with a short architecture overview | 1 | YYYY-MM-DD |  |
| RBAC matrix and security notes | One table in /docs | 2 | YYYY-MM-DD |  |
| Logging policy | One page: what is audited and what goes in the transmittal | 5 | YYYY-MM-DD |  |
| Notification catalogue | One table: event, recipient, message | 6 | YYYY-MM-DD |  |
| Test plan and UAT scripts | One page plus one script per scenario | 1, executed in 8 | YYYY-MM-DD |  |
| Runbook | Deploy, backup and restore, rollback, common problems | 9 | YYYY-MM-DD |  |
| User manual and admin guide | Short guides with screenshots | 8 to 9 | YYYY-MM-DD |  |
| Release notes | Changelog in the repository | Each release | YYYY-MM-DD |  |

Skipped on purpose: a separate architecture document, a traceability matrix and detailed test case documents. The tests and the OpenAPI spec do those jobs.

## 10. Engineering standards for one developer

- Branching: main is always deployable. Use short branches and open a pull request to yourself so CI runs and the history stays readable; squash merge.

- Self-review before every merge: read your own diff once; tests pass; migration included; OpenAPI regenerated; audit and transmittal entries written; no secrets or document content in logs.

- Definition of ready: acceptance criteria written and the API shape agreed before you start.

- Definition of done: merged, tests passing, deployed to Staging, documentation updated if behavior changed.

- Database changes only through Flyway migrations. Never edit a migration that has been applied.

- Re-plan at double: if a task takes twice its estimate, stop, note why, and re-plan before continuing.

- Keep a one-line daily journal of what you did and what is next. It saves time when you switch tasks or return after a break.

- Pin dependencies, update them once a month, and scan before each release.

- Continuity: code in a client-accessible repository, credentials in a shared password manager, backups restore-tested monthly.

## 11. Testing strategy

Test where a bug costs the most and where a solo developer is least likely to catch it by eye.

| Level | Scope | Target |
| --- | --- | --- |
| Unit | State machine, status derivation, hash chain, permission rules | Every transition and rule; most tests go here |
| Integration | Controllers against a real database (Testcontainers), allowed and denied per role | Every endpoint |
| End to end | Three browser smoke tests (Playwright): login, core scenario, rejection and resubmit | Run on Staging before each demo |
| Security | OWASP checklist, dependency scan, upload handling | Phase 8 |
| Performance | List and search with seeded volume | Phase 8, one check |
| UAT | Real users, scripted scenarios | Phase 8 |

Skipped on purpose: exhaustive screen component tests and load testing, unless the client's volume requires them.

## 12. Risks

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Scope creep from the client | High | High | Scope tiers approved in Phase 0; new requests go to the decision log and the Later tier |
| R2 | One person: illness, leave or departure stops the project | Medium | High | Client-accessible repository and credentials, README, runbook, decision notes; agree a backup contact |
| R3 | Estimates too optimistic | High | Medium | 20% buffer, timeboxes, cut-first lists, re-plan at double |
| R4 | Routing rules turn out more complex (D1, D3) | Medium | High | Settle in Phase 0; keep one tested state machine class |
| R5 | No second reviewer, so bugs and security gaps slip through | Medium | High | Self-review checklist, strong automated tests, scans, optional paid one-day review before go-live |
| R6 | Client unavailable for demos and UAT | Medium | High | Book the dates in Phase 0 |
| R7 | SSO or Active Directory details arrive late | Medium | Medium | Keep authentication behind an interface; start with local accounts |
| R8 | Support requests interrupt build time, especially after go-live | Medium | Medium | Hypercare window, written response times, requests logged on the board |
| R9 | File storage fills up or is lost | Low | High | Backup plan, monthly restore test, storage monitoring |

## 13. Decision log

| Date | Decision | Decided by | Notes |
| --- | --- | --- | --- |
| YYYY-MM-DD |  |  |  |
| YYYY-MM-DD |  |  |  |

## 14. Milestones and client approvals

| Milestone | Target date | Actual date | Approved by | Approval (email or signature) |
| --- | --- | --- | --- | --- |
| M0: Scope approved | YYYY-MM-DD |  |  |  |
| M1: Skeleton running on Staging | YYYY-MM-DD |  |  |  |
| M2: Secure login and roles | YYYY-MM-DD |  |  |  |
| M3: Create and view documents | YYYY-MM-DD |  |  |  |
| M4: Core scenario demo, end to end | YYYY-MM-DD |  |  |  |
| M5: Full traceability | YYYY-MM-DD |  |  |  |
| M6: Alerts and overdue tracking | YYYY-MM-DD |  |  |  |
| M7: Feature complete | YYYY-MM-DD |  |  |  |
| M8: UAT sign-off | YYYY-MM-DD |  |  |  |
| M9: Go-live | YYYY-MM-DD |  |  |  |

## 15. Weekly plan and client update template

| Item | Entry |
| --- | --- |
| Week ending | YYYY-MM-DD |
| Hours worked and planned |  |
| Done this week |  |
| Next week (three items at most) |  |
| Blockers and decisions needed from the client |  |
| New or changed risks |  |
| Buffer remaining | ___ of 4 weeks |
| Schedule | On track, at risk or behind |