# PHLPOST Document Tracking System: Development Plan

Internal document routing, approval and audit system. Rebuild of the prototype on the restructured schema (Document, Version, Route, RouteStep, Transmittal, AuditLog).

## 1. Document control

| Field | Value |
| --- | --- |
| Project | PHLPOST Document Tracking System v2 |
| Document version | 0.1 (draft) |
| Prepared | 2026-10-14 |
| Author / Tech lead | ____ |
| Client sponsor | ____ |
| Product owner (client side) | ____ |
| Planned start | YYYY-MM-DD |
| Planned go-live | YYYY-MM-DD |
| Status | Draft, awaiting client review |

### Revision history

| Version | Date | Author | Change |
| --- | --- | --- | --- |
| 0.1 | 2026-10-14 | ____ | Initial plan |
|  | YYYY-MM-DD |  |  |

## 2. Purpose and scope

Goal: track every document passing through every department, from creation to completion, with a full custody trail.

Core scenario the system must support: Department X creates a document and routes it to Office A and Office B for signature (or other actions). Each office acts in turn. When all steps are done, the document returns to the origin office as completed. If any office rejects or returns it, it goes back to the origin for revision and can be resubmitted as a new routing round.

In scope: authentication and roles, document and file versioning, routing engine, transmittal (custody) log, audit log, notifications and due dates, search, archive and retention, admin pages, reports.

Out of scope for v1 (backlog): certificate-based digital signatures, mobile app, external (non-staff) users, OCR or full-text search of file contents, integration with other PHLPOST systems.

## 3. Success criteria

- A user can create, route, act on, return and complete a document end to end without developer help.

- Every state change produces a transmittal entry and, where relevant, an audit entry, written in the same transaction.

- No file can change after upload without producing a new version with a new hash.

- Users only see documents they are allowed to see (role, department, access grant).

- Overdue steps are visible to the approver and the origin office.

- UAT signed off by the client with no open critical or high defects.

## 4. Open decisions to settle with the client

Phase 0 cannot close until each of these has an answer. Record the answer and date in the decision log (section 12).

| # | Decision | Options | Answer | Date |
| --- | --- | --- | --- | --- |
| D1 | Route order | Sequential only, or sequential plus parallel groups |  |  |
| D2 | What "signed" means | Recorded approval click, signature image on PDF, digital certificate |  |  |
| D3 | Rejection behavior | Back to origin (assumed), or back to previous step |  |  |
| D4 | Physical copies | Digital only, or paper tracked by QR/barcode |  |  |
| D5 | Confidential documents | Visible to route participants only? Who else? |  |  |
| D6 | Sign-in method | Local accounts, or SSO / Active Directory |  |  |
| D7 | Retention periods | Per document type |  |  |
| D8 | Email notifications | In-app only, or in-app plus email (SMTP available?) |  |  |
| D9 | Hosting | On-premise server, or cloud; file storage location (NAS?) |  |  |

## 5. Technology and environments

| Layer | Choice |
| --- | --- |
| Frontend | Vue 3, Vue Router, Tailwind, Heroicons, Axios (existing prototype is reused) |
| Backend | Spring Boot, Spring Security, Spring Data JPA, Lombok |
| Database | Relational (MySQL or PostgreSQL), schema managed by Flyway migrations. Turn off Hibernate ddl-auto |
| File storage | Local or NAS path, outside the web root, addressed by documents/YYYY/MM/DD/{id}_{name} |
| API contract | OpenAPI (springdoc), reviewed before each phase's frontend work |
| CI | Build, unit tests and lint on every pull request |

| Environment | Purpose | URL | Owner |
| --- | --- | --- | --- |
| Local | Developer machines | localhost | Developers |
| Dev | Integration, shared | ____ | ____ |
| Staging | UAT and demos, production-like | ____ | ____ |
| Production | Live | ____ | ____ |

## 6. Roadmap overview

Durations are estimates assuming one to two developers working full time. Fill in actual dates once the team and start date are confirmed.

| Phase | Name | Est. effort | Start | End | Milestone |
| --- | --- | --- | --- | --- | --- |
| 0 | Discovery and requirements sign-off | 1 wk | YYYY-MM-DD | YYYY-MM-DD | M0: Requirements baselined |
| 1 | Foundation and API contract | 1 wk | YYYY-MM-DD | YYYY-MM-DD | M1: Skeleton running in Dev |
| 2 | Authentication, users and roles | 2 wks | YYYY-MM-DD | YYYY-MM-DD | M2: Secure login and RBAC |
| 3 | Documents and file versions | 2 wks | YYYY-MM-DD | YYYY-MM-DD | M3: Create and view documents |
| 4 | Routing engine | 3 wks | YYYY-MM-DD | YYYY-MM-DD | M4: End-to-end routing demo |
| 5 | Transmittal and audit logging | 2 wks | YYYY-MM-DD | YYYY-MM-DD | M5: Full traceability |
| 6 | Notifications and due dates | 1.5 wks | YYYY-MM-DD | YYYY-MM-DD | M6: Alerts and overdue tracking |
| 7 | Search, archive, retention, admin, reports | 2 wks | YYYY-MM-DD | YYYY-MM-DD | M7: Feature complete |
| 8 | Hardening, QA and UAT | 2 wks | YYYY-MM-DD | YYYY-MM-DD | M8: UAT sign-off |
| 9 | Deployment and go-live | 1 wk | YYYY-MM-DD | YYYY-MM-DD | M9: Live, then hypercare |
|  | Total (approx.) | 17 to 18 wks |  |  |  |

Phases 2 to 7 each end with a demo to the client on Staging. Do not start a phase's frontend work until its API contract is merged.

## 7. Phase details

Each phase lists tasks, deliverables and exit criteria. A phase is done only when every exit criterion is met.

### Phase 0: Discovery and requirements sign-off

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Walk the client through the core scenario and the proposed schema.

- Resolve decisions D1 to D9.

- Write user stories with acceptance criteria for each role (Staff, Approver, Records, Admin).

- Agree the document statuses and routing rules (state machine).

- Review prototype screens and mark each as keep, adapt or replace.

Deliverables: requirements document, user story backlog, state machine diagram, decision log, client-approved scope.

Exit criteria: client signs off requirements; backlog is prioritized; open decisions are closed or have an owner and date.

### Phase 1: Foundation and API contract

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Repository setup (frontend and backend), branching strategy, pull request template.

- CI pipeline and Dev environment.

- Flyway baseline migration for the new schema; remove ddl-auto.

- Configuration per environment; secrets kept out of the repository.

- Global error format, validation, logging (with request IDs), health endpoint.

- Define request and response DTOs for all entities and publish them as OpenAPI.

- Frontend: src/api/ layer, shared axios instance, environment config, remove starter scaffolding and duplicate components.

Deliverables: running skeleton in Dev, OpenAPI spec v1, data dictionary, README with setup steps.

Exit criteria: a new developer can clone, run and test in under 30 minutes; CI is green; API contract reviewed.

### Phase 2: Authentication, users and roles

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Login and logout (JWT or session, or SSO per D6); password hashing with BCrypt; lockout after repeated failures.

- Replace CurrentUserService stand-in and permitAll() with real authorization.

- Roles: Staff, Approver, Records, Admin. Method-level checks in the service layer.

- Department and user management (admin).

- Frontend: login page, auth store, route guards, axios token interceptor, role-aware sidebar.

- Audit entries for login, logout and failed attempts.

Deliverables: RBAC matrix (role by action), security design note, working login flow.

Exit criteria: every endpoint rejects unauthenticated calls; role tests pass; admin can create departments and users.

### Phase 3: Documents and file versions

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Create and edit documents in DRAFT status (replaces the Draft table).

- Human-readable reference numbers (department code, year, running counter).

- File upload with size and type limits, SHA-256 hash, storage outside web root, authenticated download.

- Document versions (original, revision, signed) with version history.

- Frontend: Create Document wizard (details, files), My Docs, Document detail with versions card and comments.

- Audit entries for view, download and upload.

Deliverables: document and version endpoints, updated screens, storage design note.

Exit criteria: a user can create a draft, attach a file, see its hash and version history, and download it; unauthorized users cannot.

### Phase 4: Routing engine

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Route and RouteStep model with sequential order and optional parallel groups.

- Actions: submit, receive, approve or sign, reject, return for revision, recall, resubmit (new round), complete.

- One state machine class owns all status changes. Document status is derived from steps, never set directly.

- The API returns allowedActions for the current user on each document.

- Frontend: route builder, route progress card, action dialog (approve with optional signed file, reject with required reason), Awaiting My Action inbox, dashboard counters.

- Concurrency control (optimistic locking) so two people cannot act on the same step.

Deliverables: state machine document, routing endpoints, updated screens, automated tests covering every transition.

Exit criteria: the core scenario runs end to end (X to A to B to X), including a rejection and resubmission; illegal transitions are blocked and tested.

### Phase 5: Transmittal and audit logging

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Transmittal entry for every routing event, with transmittal number and hash chain (previous hash plus current hash).

- Written in the same database transaction as the action it records.

- Database permissions: application account cannot update or delete transmittal rows.

- Chain verification job and admin screen to run it.

- Audit log coverage review (login, view, download, denied access, role changes) with IP and user agent.

- Frontend: Transmittal log with filters, per-document timeline, File Integrity page showing hash and chain checks.

Deliverables: logging policy (what is logged and why), verification tool, updated screens.

Exit criteria: tampering with a transmittal row is detected by the verification job; every action in the RBAC matrix has an audit or transmittal record.

### Phase 6: Notifications and due dates

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- In-app notifications for assigned, completed, rejected and recalled events.

- Due dates on steps, overdue flag, scheduled reminder job, optional escalation to the department head.

- Email delivery if D8 requires it.

- Frontend: working bell and unread badge, Notifications page, overdue indicators.

Deliverables: notification catalogue (event, recipient, message), scheduler configuration.

Exit criteria: each event in the catalogue notifies the right people exactly once; overdue steps are flagged and reminded.

### Phase 7: Search, archive, retention, admin and reports

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Search and filters by reference number, title, type, department, status and date range; pagination everywhere.

- Archive as a separate flag, retention date, legal hold, soft delete only.

- Document access grants (viewer groups) and confidentiality levels.

- Admin: action codes, document types, retention rules.

- Reports: documents by status, average turnaround per department, overdue steps, volume over time.

Deliverables: feature-complete build on Staging, report definitions.

Exit criteria: all backlog items marked must-have are done; remaining items are logged for v1.1.

### Phase 8: Hardening, QA and UAT

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Regression test run, security review (OWASP top 10 checklist), dependency scan.

- Performance check with realistic data volume (for example 50,000 documents).

- Accessibility and browser checks.

- UAT with real client users using the test scripts; defect triage and fixes.

- Backup and restore test.

Deliverables: test report, security review notes, UAT sign-off form, known issues list.

Exit criteria: no open critical or high defects; client signs UAT.

### Phase 9: Deployment and go-live

Dates: Start YYYY-MM-DD, End YYYY-MM-DD

Tasks

- Production environment, TLS, backups, monitoring and log retention.

- Data setup: departments, users, action codes, document types. Migrate existing records if any.

- User training sessions, user manual and admin guide handed over.

- Go-live checklist, rollback plan, hypercare period (suggest two weeks) with a defined support contact.

Deliverables: deployment runbook, rollback plan, trained users, release notes v1.0.

Exit criteria: system live; hypercare issues tracked; handover accepted.

## 8. Documentation set

These are the documents to produce and keep current. Each is owned by someone and dated.

| Document | Purpose | Produced in phase | Owner | Due | Status |
| --- | --- | --- | --- | --- | --- |
| Requirements and user stories | What the system must do, with acceptance criteria | 0 |  | YYYY-MM-DD |  |
| Decision log | Record of client decisions and dates | 0 onward |  | YYYY-MM-DD |  |
| State machine specification | Allowed statuses and transitions | 0, refined in 4 |  | YYYY-MM-DD |  |
| ERD and data dictionary | Tables, columns, rules | 1 |  | YYYY-MM-DD |  |
| API contract (OpenAPI) | Endpoints and DTOs, shared by frontend and backend | 1, updated each phase |  | YYYY-MM-DD |  |
| Architecture overview and ADRs | Key technical choices and the reasons | 1 onward |  | YYYY-MM-DD |  |
| README and setup guide | Run the project locally | 1 |  | YYYY-MM-DD |  |
| Security design and RBAC matrix | Who can do what | 2 |  | YYYY-MM-DD |  |
| Logging policy | What is audited and what is in the transmittal | 5 |  | YYYY-MM-DD |  |
| Notification catalogue | Events, recipients, messages | 6 |  | YYYY-MM-DD |  |
| Test plan and test cases | How quality is checked | 1, executed 8 |  | YYYY-MM-DD |  |
| UAT scripts and sign-off form | Client acceptance | 8 |  | YYYY-MM-DD |  |
| Deployment runbook and rollback plan | Release and recovery | 9 |  | YYYY-MM-DD |  |
| User manual and admin guide | Training and day-to-day use | 8 to 9 |  | YYYY-MM-DD |  |
| Release notes and changelog | What changed in each version | each release |  | YYYY-MM-DD |  |
| Risk register | Risks and mitigations | 0 onward |  | YYYY-MM-DD |  |

## 9. Engineering standards

- Branching: main is always deployable; short-lived feature branches; pull request required with at least one review.

- Commits: small and descriptive, referencing the story ID.

- Definition of ready (a story can start): acceptance criteria written, API contract merged, design agreed.

- Definition of done (a story is finished): code reviewed, tests written and passing, API spec updated, audit and transmittal behavior verified, documentation updated, demoed on Dev.

- Database changes: only through Flyway migrations; never edit a migration that has been applied.

- Logs and data: no passwords, tokens or document contents in logs.

- Dependencies: pinned versions; scanned for known vulnerabilities each phase.

## 10. Testing strategy

| Level | Scope | Target |
| --- | --- | --- |
| Unit | Services, state machine, hash chain, status derivation | Every transition and rule covered |
| Integration | Controllers with a real test database, security rules per role | Every endpoint, allowed and denied |
| End to end | Core scenario and rejection scenario in the browser | Run on Staging before each demo |
| Security | Authentication, authorization, upload handling, OWASP checklist | Phase 8 |
| Performance | List and search endpoints with realistic data | Phase 8 |
| UAT | Real users, scripted scenarios | Phase 8 |

## 11. Risks

| # | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | Requirements change after build starts | High | High | Sign-off in Phase 0; change requests go through the decision log |  |
| R2 | Routing rules turn out more complex than assumed (D1, D3) | Medium | High | Settle in Phase 0; build the state machine as one tested class |  |
| R3 | SSO or Active Directory details arrive late | Medium | Medium | Keep authentication behind an interface; start with local accounts |  |
| R4 | Client users unavailable for demos and UAT | Medium | High | Book demo and UAT dates in this plan now |  |
| R5 | Audit and transmittal bolted on late | Medium | High | Built in Phases 3 to 5, written in the same transaction as each action |  |
| R6 | File storage grows or is lost | Low | High | Backup plan and storage monitoring before go-live |  |
| R7 | Single developer is unavailable | Medium | High | Documentation kept current; pull request reviews spread knowledge |  |

## 12. Decision log

| Date | Decision | Decided by | Notes |
| --- | --- | --- | --- |
| YYYY-MM-DD |  |  |  |
| YYYY-MM-DD |  |  |  |

## 13. Milestones and sign-offs

| Milestone | Target date | Actual date | Approved by | Signature |
| --- | --- | --- | --- | --- |
| M0: Requirements baselined | YYYY-MM-DD |  |  |  |
| M1: Skeleton running in Dev | YYYY-MM-DD |  |  |  |
| M2: Secure login and RBAC | YYYY-MM-DD |  |  |  |
| M3: Create and view documents | YYYY-MM-DD |  |  |  |
| M4: End-to-end routing demo | YYYY-MM-DD |  |  |  |
| M5: Full traceability | YYYY-MM-DD |  |  |  |
| M6: Alerts and overdue tracking | YYYY-MM-DD |  |  |  |
| M7: Feature complete | YYYY-MM-DD |  |  |  |
| M8: UAT sign-off | YYYY-MM-DD |  |  |  |
| M9: Go-live | YYYY-MM-DD |  |  |  |

## 14. Weekly status report template

| Item | Entry |
| --- | --- |
| Week ending | YYYY-MM-DD |
| Phase and progress |  |
| Completed this week |  |
| Planned next week |  |
| Blockers and decisions needed |  |
| New or changed risks |  |
| Schedule status | On track, at risk or late |